## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Issue Completing the Execution Plan | 17/03/2019 | All team members were not aware and unsure of how to prepare the execution plan. | This lead to conducting meeting and making team members aware of the plan. | Team Members | Project Manager | In Progress
IS02 | Issue Completing the Bug Report | 17/03/2019 | All team members were not aware and unsure of how to prepare a bug report | This lead to conducting meeting and making team members aware on how to create a Bug Report. | Team Members | Project Manager | Resolved
IS03 | Making of a draft report for the project sponser | 17/03/2019 | The Team memberswere not sure on what to present on the report is it a report or a ppt | This lead to dealy in presenting the report to the project sponser | Team Members | Project Manager | Resolved

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | The team emmbers were made aware on how to create an execution plan and work on it. | 17/03/2019 | All team members now know how to create an Execution plan and xan now work on it asap. | Project Manager | In Progress
IS02 | IS02 | The team emmbers were made aware on how to create an bug report and work on it. | 17/03/2019 | All team members now know how to create a big report so that to keep track of the bugs in the system. | Project Manager | Resolved
IS03 | IS03 | The team members were made aware on what to present infront of the project sponser. | 17/03/2019 | The team members now know what to present so they can work on it for the project sponser. | Project Manager | Resolved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 17/03/2019 | The team members were decided to work togather so that all problems faced can be taught and learned by coleagues. | All team members worked togather and helpled each other lear what they previously did not knew
IS02 | 17/03/2019 | The team members were decided to work togather so that all problems faced can be taught and learned by coleagues. | All team members worked togather and helpled each other lear what they previously did not knew
IS03 | 17/03/2019 | The project manager worked on what and how to present and told them to the team members. | Team members now know what their project sponser know and what they expect so they can work upon that.

## Team
INFO6068 | Capstone Project
Team Name: | Bug Slayers
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri