## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Incomplete Test Case and Test Script | 24/03/2019 | The test case and the test script was not complete as required | This lead to delay in the project and more time was required form each team member in editting the test case and test scripts. | Project Sponser | All Team Member | In Progress
IS02 | Unclear conditions on Project Execution Plan | 24/03/2019 | The team members were unclear about how to prepare the execution plan | This lead in the dealy of the work as all team members were made to do the things to be done to prepare the execution plan | All Team Members | Project Manager | In Progress
IS03 | Failure in Conducting Meeting | 24/03/2019 | The meeting was not conducted due to unavailibility of the Project Manager and other team members. | Problems in work distribution and working on Test Case and Test Scripts along with preperation of execution plan | All Team Members | All Team Member | In Progress

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | All team members were instructed to get togather and complete the remaining work as soon as possible | 24/03/2019 | Completion of the remaining work and moving towards the execution plan to get the project back on track | Project Manager | In Progress
IS02 | IS02 | All team members were gathered and made open to discuss thing they had problem with and fellow helped them solve those | 24/03/2019 | All team members were aware of the tasks to perform | Project Manager | In Progress
IS03 | IS03 | Conducted meeting with those who are available and discussed things that are supposed to be done by them. | 24/03/2019 | Misscommunication of the work distribution and late completion consuming more time | Project Manager | In Progress

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 24/03/2019 | To complete the reamining part in the test case and test script and to edit the tasks to go further in the project | All team members worked more than usual to complete the work and move to the next one.
IS02 | 24/03/2019 | Project manager handled the situation and got the team member togather for increasing their knowledge on the plan | All team member learned the task to perform and go to complete the execution plan.
IS03 | 24/03/2019 | All further meeting should be conducted on time and planned way ahead of time keeping in mind avaibility of all team members | Team members were aware about being on time in future meetings

## Team
INFO6068 | Capstone Project
Team Name: | Bug Slayers
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri