## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Completion of final presentation and report | 07/04/2019 | The final documentation of the project delayed due to work load | This lead to rescheduling and managing time in various other work. | Project Sponser | All Team Member | In Progress

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | All team members were instructed to manage their work accordingly and were encouraged to complete their work early before time | 07/04/2019 | The work load lead to some serious scheduling and managing tasks which even affected the personal life of the team members. | Project Manager | In Progress

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 07/04/2019 | To complete the work on time team members were encouraged to work afterhours and even on weekends so that the work gets completed on time. | All team members are working at their best to complete the work on time and produce a good outcome of the project.

## Team
INFO6068 | Capstone Project
Team Name: | Bug Slayers
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri