## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Project Manager fell sick. Need someone to take charge. | 21/1/2018 | There is a concern that Harshita is sick and she may take time to recover. This can delay the project planning. | Project planning can be delayed and this may in turn delay project completion. | Harshita Saggu | Harshita Saggu | Approved
IS02 | Team needs training on Apache Tomcat | 21/1/2018 | No previous experience of working with the software | If not addressed, this issue can affect project progress. | Harshita Saggu | All | Processing
IS03 | Non-compliance with team policies | 21/1/2018 | Not following team rules | Can lead to unethical team culture and conflict | Jay Magnani | All | Approved
IS04 | Conflict in assigning role of automation tester | 21/1/2018 | 2 team members have equal experience in Automation Testing and want to be considered for the same. However, only one is needed. The other has to work as a Manual Tester. | Dissatisfaction with allocated responsibilities may lead to inefficient work and unhealthy work environment. | Sohana Kadiwala | Sohana Kadiwala, Jay Patel | Project Manager
IS05 | Unavailability of up to date hardware resources. | 21/1/2018 | 2 team members have old laptops which work slow. | This can slow down the team performance. | Jay Patel | Harshita Saggu, Jenab Vohra | Processing
IS06 | Availability for meetings differ for the team members | 21/1/2018 | One common time slot has to be figured out to have regular weekly meetings | Difficult to schedule meetings | Jay Magnani | All | Processing
IS07 | Meeting milestones and project deadlines | 21/1/2018 | To make sure, the project runs smoothly, all team members need to make sure they complete the tasks before the due date and time. | Project completion and delivery will be affected. | Jenab Vohra | All | Approved
IS08 | Absence from meetings without advance notification. | 21/1/2018 | Absence from meetings except in case of an emergency is a serious non- compliance with the team policy | The absentee may lag behind because of missing out on certain details discussed in meeting. | Jay Magnani | All | Processing
IS09 | Addition of a new team member. Conflict in deciding her role. | 21/1/2018 | All team members have been assigned roles and a sudden addition of a new team member can jeopardize the planning done so far. | Confusion can arise and there can be chances of conflict. | Jenab Vohra | Riddhi Khatri | Approved
IS10 | Seeking external help/ expert advice for problem solving | 21/1/2018 | If there is a problem outside the experience and knowledge of team members , what could be the available resources. | Can hinder the team's progress | Riddhi Khatri | All | Processing

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | Transfer of responsibility of Project Manager's role to Jenab Vohra. Transfer of responsibility of Programmer's role to Harshita. | 21/1/2018 | All the team members agreed with the decision | All Team Members | Approved
IS02 |  | Training material will be supplied to the team and also practical sessions will be facilitated by the Product Owner. | 21/1/2018 | Understanding of the project will be clear and can be implemented with help of product owner | All Team Members | Processing
IS03 | IS03 | After discussing with the team, penalty will be imposed. | 21/1/2018 | Everyone should attend the meeting and be on time | All Team Members | Processing
IS04 | IS04 | Sohana assigned as the role of Manual Tester and Jay Patel assigned as the role of Automation Tester after properly discussing their project experience and qualifications. | 21/1/2018 | Changes of the responsibilities which are good for better understanding with knowledge they have | Jenab Vohra | Approved
IS05 | IS05 | Team members will be supportive at all times and can lend their own laptops when not being used. | 21/1/2018 | If any laptop crash then every one can help that person and resolve the problems | Jay Mangnani | Processing
IS06 | IS08 | Available time slots for all team members have been noted. | 21/1/2018 | All the team members will be present in meeting | Jenab Vohra | Approved
IS07 | IS07 | Deadlines for tasks will be set a few days before the actual milestone to make sure there is a time buffer available for emergencies. | 21/1/2018 | Tasks will be completed withing the deadlines | Jenab Vohra | Processing
IS08 | IS06 | Meeting attendance has been made mandatory. | 21/1/2018 | Everyone will become puntual | Jay Mangnani | Approved
IS09 | IS09 | Riddhi Khatri assigned the role of Tech Lead. | 21/1/2018 | To reduce the risks for installing application in each members laptop | Jenab Vohra | Approved
IS10 | IS10 | Product Owner can be contacted for expert advice and also, team can seek advice from other testing teams. | 21/1/2018 | Project goals will be achived without any failure | All Team Members | Approved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 21/1/2018 | Jenab assigned as Project Manager and her role of programmer is taken by Harshita. | Transfer of responsibilities and tasks from Harshita to Jenab and vice versa | IS01
IS02 | 21/1/2018 | Roles and responsibilities: Harshita- Programmer, Sohana-Manual Tester, Jay Patel-Automation Tester, Jay Mangnani -Scribe and Documentation Lead | To work in the field where all are better then other team members | IS04
IS03 | 21/1/2018 | Established rule to be on time for meetings | Work can be done collectively without wasting time | IS06
IS04 | 21/1/2018 | Established rule to communicate in universal language English. | Every one can understand each others point of view
IS05 | 21/1/2018 | Created a Whatsapp group to communicate with each other. | To communicate with each other easily
IS06 | 21/1/2018 | Riddhi assigned as Tech Lead. | Saved trouble of deciding roles again | IS09
IS07 | 21/1/2018 | By next monday, all software requirements need to be fulfilled | All applications will be installed and resource requirements will be completed by next meeting. | IS05

## Team
INFO6068 | Capstone Project
Team Name: | Bug Slayers
Members: | Harshita Saggu
Sohana Kadiwala
Jenab Vohra
Jay Magnani
Jay Patel
Riddhi Khatri