## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | The installation of environment in each team members | 2019-01-28 | The apache tomcat server need to be installed in everyone for testing the website | Time consumed in installation | All the team members | Project Manager | Approved
IS02 | Inoperative errors in running the sql datbase | 2019-01-28 | The SQL databse which we chose to run on the apache server was not supporting the local host file | The delay in cause the slow performance and conducting meeting with extra minutes | All the team members | Project Manager | Processing
IS03 | Contrasting opnion on the application installed | 2019-01-28 | The views on the website where not as expected , delay in making plan about testing | The team performace have to pay for it | All the team members | Every team member | Processing
IS04 | Availability for meetings differ for the team members | 2019-01-28 | One common time slot has to be figured out to have regular weekly meetings | Difficult to schedule meetings | All the team members | Every team member | Processing
IS05 | Understanding about test stratergy | 2019-01-28 | Different parts of the test stratergy components that are not clear to understand. | Tough to write and developing test strategy. | All the team members | Every team member | Processing
IS06 | Seeking help from outside every time | 2019-01-28 | Unable to understand test stratergy and build it so it makes need an external help from the other people | Project completion and delivery will be affected. | All the team members | Every team member | Approved
IS07 | Failure in meeting | 2019-01-28 | The meeting was not conducted as team members were unable to meet on the respective time | Hindrance in writing the test strategy | All the team members | Every team member | Not conducted

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | With eachother help everyone had installed the enviroment in their laptops | 2019-01-28 | The installation was done but it was not as expected to time schedule | All | Completed
IS02 | IS02 | The SQL database was connected to the server with support of the team. | 2019-01-28 | The SQL server was running on the apache server | All | Completed
IS03 | IS03 | Project manager took the decision by the majority was there | 2019-01-28 | The team came to the conclusion about the application reviews | All | Completed
IS04 | IS04 | Decided the time slot every week that everyone need to attend the meetings | 2019-01-28 | Everyone should attend the meeting and be on time | All | Completed
IS05 | IS05 | Asking project owner about some issues developed while discussing test stratergy | 2019-01-28 | Developing the test stratergy | All | Processing
IS06 | IS07 | Warning given and the meeting will be reconducted | 2019-01-28 | Everyone agreed to the action taken | All | Completed

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 2019-01-28 | The meeting will be conducted and everyone need to be present | Everyone respected that decision | IS07
IS02 | 2019-01-28 | Before every meeting each and every member has to do some research and give viwes on the application | Disagree on this decision but need to follow
IS03 | 2019-01-28 | Ask the expericend people about the concept of building test startegy | Time consuming and delay in the performance | IS05
IS04 | 2019-01-28 | Detection of the flaws from the application will be conducted earlier than schedule | The performance which was delayed will be back on the path as decided earlier.
IS05 | 2019-01-28 | Try to sort the problems without much external help | More time to give on project
IS06 | 2019-01-28 | Using of selenium tool for automation testing | Automation testing of the application which will make our work easy

## Team
INFO6068 | Capstone Project
Team Name: | Bugs Slayer
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri