## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Preparing Test Strategy | 2019-02-02 | Understanding the concepts included in Test Strategy | Time consumed | All the team members | Project Manager | Approved
IS02 | Distributing the contents of Test Strategy | 2019-02-02 | Project Manager assigned the work equally | The work was distributed equally with time | Jay Mangnani | Project Manager | Approved
IS03 | Understanding of Test Data | 2019-02-02 | To find and collect the data required for test | time consuming for collection of test data | Sohana Kadiwala | Every team member | Approved
IS04 | Differntiate the process of Exit and Entry criteria | 2019-02-02 |  | Difficult for the exit criteria | Harshita Saggu | Every team member | Approved
IS05 | Understanding about the management tools | 2019-02-02 | To get the knowledge of management and automation tools for testing | All team members understand the tools | Jay Patel | Every team member | Approved
IS06 | To discuss project plan | 2019-02-02 | To get the details of the project plan with all team members | Understand the project plan | Jenab Vohra | Every team member | Processing
IS07 | Team member laptop crash | 2019-02-02 | Wi-fi failed and was not able to communicate via skype | loss in communication and delay in work assigned | Harshita Saggu | Every team member | Processing
IS08 | Conflict between the work with other projects | 2019-02-02 | Work load increased | No impact on overall project | Jenab Vohra | Every team member | Approved

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | Internally discussion with team members | 2019-02-02 | Work completed with more time | All | Completed
IS02 | IS02 | Project Manager assigned work to every team member equally | 2019-02-02 | To complete the Test Strategy within given time | All | Completed
IS03 | IS06 | to go thorugh the project plan template and discuss | 2019-02-02 | To get details of the concepts and work required to complete project plan | All | Completed
IS04 | IS07 | Working with other friends laptop | 2019-02-02 | Slight delay in work | All | Completed
IS05 | IS08 | To go thorugh the online lecture and understand Test Strategy | 2019-02-02 | Work completed with understanding or every team member | All | Working

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 2019-02-02 | The meeting will be conducted and everyone need to be present | Everyone respected that decision
IS02 | 2019-02-02 | To work on project plan as soon as possible | All team members were agreed with decesion | IS06
IS03 | 2019-02-02 | Team member will get new laptop ASAP | Communication will be easy | IS07
IS04 | 2019-02-02 | Getting the deep knowledge about contents of Test Strategy | Meet the deadline | IS03, IS04, IS05

## Team
INFO6068 | Capstone Project
Team Name: | Bugs Slayer
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri