## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | The division of the work in the project plan | Work will be distributed equally and each team member will contribite his part | The division of the work of the project plan was a major issue of who will take which part and present. | This resulted in loss of time in deciding the work to be distributed and even led to know the positives and negatives of each team members. | All Team Members | Project Manager | Resolved
IS02 | Lack of research and information gathering in the project plan | 29/01/2019 | The issue of division of project plan to each team member led to lack of research and information gathering due to loss of time and lack of management. | This resulted in lack of knowledge of the topics and had issues in the presented when the Project sponser asked questions regarding this. | All Team Members | Each Team Member | In Progress
IS03 | Lack of cooperation and understanding of team members. | 04/02/2019 | The cooperation and understanding between the team members is the most important in this type of project and during the presentations. | This let to disputes regarding the topics and presentation work distribution and also it let to some work not been done by the team members | All Team Members | Each Team Member | Resolved
IS04 | Unclear about the concepts of the project | 04/02/2019 | The contents of the project is the most important thing and all the team members should be aware about this. There should be understanding of each and every word that is related to the project | This led to some team members being not able to answer some questions clearly related to the presentation like BaseLine, Grey Box and understanding the WebDrivers | All Team Members | Each Team Member | Resolved
IS05 | Problem working with the MsProject | 06/02/2019 | The familiarity with the software was not known to each and every team members as some knew only partially. | This led to loss of time and resources as those who didn't knew were made to get familiar with the software through the help of other team Members | All Team Members | Each Team Member | In Progress
IS06 | Problem working on Tracibility Matrix and Use Case. | 06/02/2019 | The Team members were unclear on how to work on developinh UseCase and Tracibility Matrix | This led to discuss and understand the work and get familiar with these this on how to use them in this project. | All Team Members | Each Team Member | In Progress
IS07 | Failure in Meeting | 09/02/2019 | The meeting was not conducted as it was unclear on which time it is going to be due to Non-availibility of the Project Manager and other team members. | Problems in work distribution and working on UseCase and Tracibility Matrix along with Ms Project | All Team Members | Each Team Member | Resolved

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | Work will be distributed equally and each team member will contribite his part | 04/02/2019 | All team members came forward during the time of next work division | All Team Members | Resolved
IS02 | IS02 | Conducted post Test Plan review and made sure that proper research made in future. | 04/02/2019 | All team members agreed on working hard next time | All Team Members | Resolved
IS03 | IS03 | Conducted post Test Plan review and made sure that every one cooperates form now on. | 04/02/2019 | All team members agreed to have cooperation in the project further. | All Team Members | Resolved
IS04 | IS04 | Conducted meeting and discussed on the concepts further deep to understand better. | 04/02/2019 | Led to reserch on the topics and understand further. | All Team Members | Resolved
IS05 | IS05 | Made sure everyone understand the concept of MsProject | 06/02/2019 | Everyone got to know the concepts of MsProjects | All Team Members | In Progress
IS06 | IS06 | Made sure everyone is familiar working with the Tracibility matrix and UseCase | 06/02/2019 | Everyone got familiar with the Tracibility matrix and UseCase diagrams | All Team Members | In Progress
IS07 | IS07 | Conducted meeting with those who are available and discussed further things | 09/02/2019 | Resulted in late decision | All Team Members | In Progress

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 04/02/2019 | Work will be distributed equally and each team member will contribite his part | All team members came forward during the time of next work division | IS01
IS02 | 04/02/2019 | All team members will do proper research and gather thorough information | All team members agreed on working hard next time | IS02
IS03 | 04/02/2019 | All team members will give equal cooperation in the project | All team members agreed to have cooperation in the project further. | IS03
IS04 | 04/02/2019 | Concepts of the project will be made clear to each and every team member. | Led to reserch on the topics and understand further. | IS04
IS05 | 06/02/2019 | Each team member should know how to work on MsProject | Everyone got to know the concepts of MsProjects | IS05
IS06 | 06/02/2019 | Each team member should be able to perform and do Tracibility Matrix and UseCase | Everyone got familiar with the Tracibility matrix and UseCase diagrams | IS06
IS07 | 09/02/2019 | All further meeting should be conducted on time and planned way ahead of time keeping in mind avaibility of all team members | Resulted in future meetings to be on schedule | IS07

## Team
INFO6068 | Capstone Project
Team Name: | Bug Slayers
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri