## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
ISS01 | Division of work | 2019-02-20 | The work was not equally divided so all the members were not happy | The meeting remained undecisive | All members | Project Manager | Pending
ISS02 | Understanding | 2019-02-20 | The test cases development had an unclear idea once all had started making it , so need more knowledge and coverage for understanding. | Took more time than needed | All members | All members | Pending
ISS03 | Complexity | 2019-02-20 | The test cases needed to cover the whole website , so almost all the data must be covered | Delay in developing them | All memebers | All members | Pending
ISS04 | Commuication Gap | 2019-02-20 | The communication channel was weaken because the reading week started. | Delay in developing them | All memebers | All members | Pending

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
AC01 | ISS01 | The work was divided equally according to everyone 's preferences | 2019-02-20 | Everyone intrested in work | Project Manager | Completed
AC02 | ISS02 | Everyone understanding played major role in this issues and it was resolved | 2019-02-20 | The work was taking its path | All members | Completed
AC03 | ISS03 | The test cases must be build according to given database | 2019-02-20 | The work will be with good coverage of website | All members | Completed

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
D001 | 2019-02-21 | The work was distributed equally with correct portion disributed | This gained the interest of all the members | ISS01
D002 | 2019-02-21 | The meeting was decided to conduct again so that the understanding of test cases is clear | More clear idea and thoughts will be developed in fresh mind | ISS02
D003 | 2019-02-21 | The database of the ewheelz was installed and made work in evryone , so it will be easy to cover all the test cases | The work will be easy and with speed | ISS03
D004 | 2019-02-21 | The meeting was rescheduled again in the reading week so that there is no communication gap because of the reading week | The work will be completed on time | ISS04

## Team
INFO6068 | Capstone Project
Team Name: | Bugs Slayers
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri