## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Conflit in developing Test Cases | 25/2/2019 | Understanding the use case and developing the test cases with data availabe | Time consuming and understanding the Test Cases | All the team members | Project Manager | Approved
IS02 | SQL database server not connected with majority of team members | 25/2/2019 | Database not connected in 4 team members | The work was distributed equally which delayed because of connection | Jay Mangnani | Project Manager | Processing
IS03 | Due to reading week communication was weaken | 25/2/2019 | The communication channel was broken | loss in communication and delay in work assigned | All the team members | Every team member | Approved
IS04 | Conflict for what to include and not in Test Cases | 25/2/2019 | Which test cases to be include with the given data | Difficulty for the data entered | All the team members | Every team member | Processing
IS05 | Many Test cases may be similar | 25/2/2019 | Test cases for Password are similar for user as well as Admin | Confusion which to include | All the team members | Every team member | Approved
IS06 | Time consuming | 25/2/2019 | To develop test cases its time consuming | Understand the Test Cases | All the team members | Every team member | Processing
IS07 | Data to entered in Test cases | 25/2/2019 | Which data should be entered in Test cases data for valid and invalid |  | Sohana Kadiwala | Every team member | Processing

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | Internally discussion with team members | 25/2/2019 | Work completed with more time | All | Completed
IS02 | IS02 | Project Manager helped every one with connection | 25/2/2019 | To get the database connection but it needs more time then scheduled | All | Completed
IS03 | IS03 | Meeting conducted and made good communication | 25/2/2019 | All team members worked together for Test Cases | All | Working
IS04 | IS05 | Include all the test cases is similar or not | 25/2/2019 | Slight delay in work | All | Completed
IS05 | IS07 | Take the data what is availabe in tables in SQL | 25/2/2019 | Work completed with understanding | All | Working
IS06 |  | Online research helped to understand the Test Cases | 25/2/2019 |  |  | Completed

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 25/2/2019 | The meeting will be conducted and everyone need to be present | Everyone respected that decision | IS03
IS02 | 25/2/2019 | To work on the connection of MySql | All team members were agreed | IS02
IS03 | 25/2/2019 | Team member will be in touch with project manager until the task is completed | Communication will go with flow | IS03
IS04 | 25/2/2019 | Getting the deep knowledge about data to be included in Test Cases | Meet the deadline | IS07
IS05 | 25/2/2019 | Most favourable Test Cases were included with data avilable | Reduce the Test Cases | IS05

## Team
INFO6068 | Capstone Project
Team Name: | Bugs Slayer
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri