## Issues
ITEM# | ISSUE | DATE | DESCRIPTION | IMPACT | RAISED BY | RESPONSIBLE | STATUS | NOTES
IS01 | Completion test cases and test script and other documents on time after updation | 10/03/2019 | The completion of phase two of test case and test script due to some issues missed in phase 1 of the project | This lead to running late and behind the time on the project | Project Sponser | All Team Member | In Progress
IS02 | Unable to conduct meetings on time | 10/03/2019 | Not able to conduct formal meeting of all team members due to personal work. | This lead to improper communication and work distribution between team members | Team Members | Project Manager | Resolved

## Actions
ITEM# | ITEM# ISSUE TAB | ACTION TAKEN | COMPLETION DATE | IMPACT | RESPONSIBLE | STATUS | NOTES
IS01 | IS01 | The project manager instructed the team members to get on and complete the remaining work to get on time with the project. | 10/03/2019 | The work load lead to rescheduling few tasks related to project, leave a few work behind to complete this one on time | Project Manager | In Progress
IS02 | IS02 | The project manager got in touch with each team member and worked upon the avaibility for the meet. | 10/03/2019 | Team members worked upon and started working their work after getting in touch with the project manager and understanding their duties. | Project Manager | Resolved

## Decisions
ITEM# | DATE | DESCRIPTION | IMPACT | ITEM# ISSUE TAB | NOTES
IS01 | 07/04/2019 | The project manager issues to all team members to complete theis thing first and then continue with the remaining work so that all things gets done one by one. | All team members worked on completing the work first and then get to other things so that the project is not left behind.
IS02 | 10/03/2019 | The project manager fixed the timings of the meeting in advance so that this time it does not happen again. | Team Members are aware of the next meet and plan well befofe.

## Team
INFO6068 | Capstone Project
Team Name: | Bug Slayers
Members: | Jenab Vohra
Jay Mangnani
Jay Patel
Harshita Saggu
Sohana Kadiwala
Riddhi Khatri