## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 108
| Number of testers | 6
| Test cycle duration | 6 days
Status for 03/31/2019
| Number of test cases planned | 18 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 15
| Number of test cases executed overall | 80
| Number of defects encountered today | 3
| Number of defect encountered so far | 30
| Number of critical defects- still open | 8
Overall status
| Number of test cases planned | 108
| Number of test cases executed | 80
| Pass Percentage of the defects | 98%
| Defects density | 2 per day
| Critical defects percentage | 26.6%
©- SoftwareTestingHelp.com

## Detailed status
Module | Test Case | Scenario | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin | Login | Login | High | Jenab | 2019-03-27 | Fail | DR_AL_01: Runs with nothing written or anything written.
Admin | Add Route | Add From_To | Medium | Jenab | 2019-03-27 | Pass
|  | Date | Medium | Jenab | 2019-03-27 | Pass
|  | Only add to one ID | High | Jenab | 2019-03-27 | Fail | DR_ONLY _ONE_ID:The whole data is entered only in one route Id and others are not working.
Admin | View Route | View Route | Complex | Jenab | 2019-03-27 | Pass
|  | Add pickuppoints | Complex | Jenab | 2019-03-27 | Pass
Admin | Delete_Route | Delete route by route id | Complex | Harshita | 2019-03-27 | Fail | D_DR_01: On selecting route id it gives exception error | Critical | Open
Admin | Delete_Travel | Delete route by travel id | Complex | Harshita | 2019-03-27 | Fail | D_DR_02: On selecting travel id it gives exception error | Critical | Open
Admin | Font _Size_ViewRoute | Font size is not consistent through out | Medium | Harshita | 2019-03-27 | Fail | D_DR_03: Font size is not consistent through out website | Critical | Open
Admin | View_Travel | ViewTravel_viewRoutes | Complex | Harshita | 2019-03-27 | Pass
|  | ViewTravel_addPickuppoint | Complex | Harshita | 2019-03-27 | Pass
Admin | Add_Travel | TravelsName | Medium | Harshita | 2019-03-27 | Fail | D_AT_01: Takes special characters and numbers that does not give good despriction of travels
|  | Location | Complex | Harshita | 2019-03-27 | Pass
|  | Address | Complex | Harshita | 2019-03-27 | Fail | D_AT_02:Takes special characters and numbers that does not give good despriction of address and confuses the reader
|  | Agent Name | Medium | Harshita | 2019-03-27 | Fail | D_AT_03:Does not take valid name , takes special charcteers , numbers and exceeds the limit more than 10
|  | Phone Number | High | Harshita | 2019-03-27 | Fail | D_AT_04:Does not take 10 digits , if one is given that is also excepted
Admin | Add_User_Admin | Add Customer | High | Jenab | 2019-03-27 | Fail | D_AU_01: This have in datbase but not in the layout, for checking the addition of the customer
User | User_Login | User login | High | Jay Mangnani | 2019-03-27 | Fail | D_US_01: User is able to login without any username and password and is directed to admin page | Critical | Open
View Testimonial | View_Testimonial | View_Testimonial | Medium | Riddhi | 2019-03-26 | Pass |  | Major | Open
View Testimonial | View_Testimonial | View_Testimonial | Low | Riddhi | 2019-03-26 | Pass |  |  | Open
Give Testimonials | Give_Testimonial | Give_Testimonial | Medium | Riddhi | 2019-03-26 | Pass
Give Testimonials | Give_Testimonial | Give_Testimonial | Medium | Riddhi | 2019-03-26 | Fail | D_GT_02: No error message is displayed eventhough the feedback provided exceeds the limit, D_GT_02: The feedback more then 200 characters given is added into the table named as feedback in the database | Major | Open
Give Testimonials | Give_Testimonial | Give_Testimonial | Medium | Riddhi | 2019-03-26 | Pass
Give Testimonials | Give_Testimonial | Give_Testimonial | Low | Riddhi | 2019-03-26 | Fail | D_GT_03: System is taking wrong email ID format and update database with the wrong/non exist email ID. | Medium | Open
Give Testimonials | Give_Testimonial | Give_Testimonial | Medium | Riddhi | 2019-03-26 | Fail | D_GT_01: No error message is displayed eventhough the feedback provided exceeds the limit, D_GT_02: The feedback more then 200 characters given is added into the table named as feedback in the database | Major | Open
| View Route | View Route | Complex | Jay Patel | 2019-03-28 | Pass
| View Route | Add pickup Points | Complex | Jay Patel | 2019-03-28 | Pass
Book Ticket | Book_Ticket | To | High | Sohana Kadiwala | 2019-03-27 | Pass | D_BT_01:Error is displayed according to input in the fields | Trivial | Open
|  | From | High | Sohana Kadiwala | 2019-03-27 | Pass | D_BT_02:Error is displayed according to input in the fields | Critical | Open
|  | Journey_Date | High | Sohana Kadiwala | 2019-03-27 | Pass | D_BT_03:Error is displayed according to input in the fields | Critical | Open
|  | Bus_Type | Medium | Sohana Kadiwala | 2019-03-27 | Pass | D_BT_04:Error is displayed according to input in the fields | Critical | Open
|  | No. of Passenger | Low | Sohana Kadiwala | 2019-03-27 | Pass | D_BT_05:Error is displayed according to input in the fields | Critical | Open
Cancel_Ticket | Cancel_Ticket | Ticket_ID | Medium | Sohana Kadiwala | 2019-03-27 | Pass | D_BT_06:Error is displayed according to input in the fields | Critical | Open
Customer_detail | Customer_Detail_Inv_Address | Address | Medium | JayMangnani | 2019-03-27 | Fail | D_CI_01: It takes the address with the charcters also | Major | Open
Customer_payment_detail | Customer_Payment_Inv_Bankame | BankName | High | JayMangnani | 2019-03-27 | Fail | D_CP_01: It take the number , charcters as the bank name | Crtical | Open
Non-Functional | Non-Functional_security |  | High | Jenab Vohra | 2019-03-27 | Fail | D_ST_01:The Admin name and password are shown in the URL | Critical | Open
Non-Functional | Non-Functional_security |  | High | Jenab Vohra | 2019-03-27 | Fail | D_ST_02:The Username name and password are shown in the URL | Critical | Open

## Bug report
Defect ID | Test Script ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
DR_AL_01 | TC_ADMIN_LOGIN_INVAL_001-008 | The username and password fields does not take any values and just directed to admin page and also if we write anything in both fields it will be directed to the admin page. | 1)http://localhost:8080/ewheelz/ 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Submit" button. 5)Directed to the admin page. Data : Username :<blank> Password:<blank> Expected Result: "Username and Password are wrong". Actual Result: Directed to Admin page. | Critical | Open | Jenab
DR_ONLY _ONE_ID | TC_ADDUSER_VAL_001 | The Add_route is having the field of Trave_Id and that are submitted only in one particular id they are not submitted in the other ids | 1)http://localhost:8080/ewheelz/ 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Submit" button. 5)Directed to the admin page. 6)Click on AddRoute. 7)Add all the valid credentials 8)Click on "Submit". Data: RFrom: Hyderabad RTo: Mumbai TravelID: T2 BusID: B3 Departure: 21:00:00 Arrival: 12:00:00 Fare: 800 JDate: 2019-03-30 Availability: 38 Expected Result: "Must be added to the databases". Actual Result: For any route added, Route id remains R1. So, Multiple routes with same id end up in the database. | Critical | Open | Jenab
D_DR_01 | TC_DELETEROUTE_INV_001 | Delete Route function generates exception on selecting any Route id and does not delete it. | 1. Login to the site with admin credentials. 2. Click on "Delete Route". 3. Select Route id 4.Click "Delete" Data: R2 from drop down menu Expected Result:"Deleted Successfully ". Actual Result: "Java Null Pointer Exception" | Major | Open | Harshita
D_DTR_01 | Test Case - TC_DELETETRAVELROUTE_VAL_001 | Delete Travel function generates exception on selecting any Travel id and does not delete it. | 1. Login to the site with admin credentials. 2. Click on "Delete Travel". 3. Select Route id: 4.Click "Delete" Data:T2 from drop down menu Excepted Result :"Deleted Successfully". Actual Result :"Java Null Pointer Exception". | Major | Open | Harshita
D_FS_01 |  | Font size of the website is not consistent with the requirements. Headings font is 9pt and text/data font size is 8 pt instead of being 10 pt throughout for all | 1. Login to the site with admin credentials. 2. Click on "View Route". 3. Right click on the web page and select "Inspect Element" 4.Check the font size of "View Route" button. 5.Check the font size of "Route id". | Trivial | Open | Harshita
D_AT_01 | TC_ADDTRAVELROUTE_INV_001 | The Field "TravelsNames" take all charcters , numbers , special charcters which does ot provide the valid information for the travels agent. | 1. Login to the site with admin credentials. 2. Click on "Add Travel Route". 3. Fill all the fields with valid credentials except the "TravelsName" 4.Clickon"Submit" 5.It adds the TravelRoute. Data:TravelsName:A!#23z) Location: Delhi Address: 787 Richmond Agent Name: KLJ Phone Number: 232-676-1000 Expected Result: "Enter proper Travel Name". Actual Result : "Added Successfully". | Major | Open | Harshita
D_AT_02 | TC_ADDTRAVELROUTE_INV_001 | The Field "Address" take all charcters , numbers , special charcters which does ot provide the valid information for the address | 1. Login to the site with admin credentials. 2. Click on "Add Travel Route". 3. Fill all the fields with valid credentials except the "TravelsName" 4.Clickon"Submit" 5.It adds the TravelRoute. Data:TravelsName:ABC Location: Delhi Address: 7123#%%#BUMI Agent Name: KLJ Phone Number: 232-676-1000 Expected Result: "Enter valid Addresss". Actual Result : "Added Successfully". | Major | Open | Jenab
D_AT_03 | TC_ADDTRAVELROUTE_INV_001 | The Field "Agent name" take all charcters , numbers , special charcters which does ot provide the valid information for the agent name | 1. Login to the site with admin credentials. 2. Click on "Add Travel Route". 3. Fill all the fields with valid credentials except the "TravelsName" 4.Clickon"Submit" 5.It adds the TravelRoute. Data:TravelsName:ABC Location: Delhi Address: 787 Richmond Agent Name: !@12Der Phone Number: 232-676-1000 Expected Result: "Enter the agent name properly". Actual Result : "Added Successfully". | Major | Open | Jenab
D_AT_04 | TC_ADDTRAVELROUTE_INV_001 | The Field "Phone number" take less than 10 digits as phn number that take 1 also | 1. Login to the site with admin credentials. 2. Click on "Add Travel Route". 3. Fill all the fields with valid credentials except the "TravelsName" 4.Clickon"Submit" 5.It adds the TravelRoute. Data:TravelsName:ABC Location: Delhi Address: 787 Richmond Agent Name: KLJ Phone Number: 2 Expected Result: "Enter the agent name properly". Actual Result : "Added Successfully". | Crirtical | Open | Harshita
D_AU_01 | TC_ADDUSER_VAL_008 | The customer table is seen in database but not anywhere in the layout , so it cannot add the customer . | 1. Goto http:/localhost:8080/ewheelz/AdminLogin.html 2. Leave username and password blank 3.Check all the modules of the admin login. 4.Check the "customer master" table from sql databases Data: select * from customermaster; Expected Result: "layout for adding customer" Actual Result: "No layout" | Critical | Open | Jenab
D_US_01 | TC_USER_LOGIN_INVAL_001-007 | User is able to login without any username and password and it is directed on admin page | 1. Goto http:/localhost:8080/ewheelz/Login.jsp 2. Leave username and password blank 3.Click on"Submit" 4.It is directed to admin page Data: Username :<blank> Password:<blank> Expected Result: "Directed to user page". Actual Result : "Directed on the admin page". | Critical | Open | Jay Mangnani
D_GT_01 | TS_INV_GT_04 | No error message is displayed eventhough the feedback provided exceeds the limit | 1: Goto the link http:///ewheelz/User.html 2: Click on User Login 3: Click on Give Testimonial button on the left side of the web page 4: Enter the emai Id "abc123@gmail.com"text in the "email Id" field 5: Enter the feedback (more than 200 characters) in the feedback field 6: Click on Submit Feedback button; Expected Result: Feedback will not be submitted and the message "Feedback cannnot be more then 200 characters" in a pop up displayed; Actual Result: The message "Your Feedback submitted successfully! Thanks for providing your feedback." is displayed at the top of the web page along with a "Back button | Major | Open | Riddhi
D_GT_02 | TS_INV_GT_04 | The feedback more then 200 characters given is added into the table named as feedback in the database | 1: Goto the link http:///ewheelz/User.html 2: Click on User Login 3: Click on Give Testimonial button on the left side of the web page 4: Enter the emai Id "fk123@gmail.com"text in the "email Id" field 5: Enter the feedback (more than 200 characters) in the feedback field 6: Click on Submit Feedback button; Expected Result: Feedback will not be saved in the table "feedback" in the data base; Actual Result: The message "Your Feedback submitted successfully! Thanks for providing your feedback." is displayed at the top of the web page along with a "Back button and the feedback given is added into the table named as feedback in the database | Major | Open | Riddhi
D_GT_03 | TS_V_GT_01 | System is taking wrong email ID format and update database with the wrong/non exist email ID. | 1.Click on the given link to open the testimonial page. 2.Click on email id to enter the email id. 3.Click on feedbak field to type the feedback. 4. Click on submit button to submit the feedback. 5.Verify with the database whether it is updated or not. | Minor | Open | Riddhi
D_GT_04 | TS_INV_GT_04 | No error message is displayed eventhough the feedback provided exceeds the limitC26 | 1: Goto the link http:///ewheelz/User.html 2: Click on User Login 3: Click on Give Testimonial button on the left side of the web page 4: Enter the emai Id "abc123@gmail.com"text in the "email Id" field 5: Enter the feedback (more than 200 characters) in the feedback field 6: Click on Submit Feedback button; Expected Result: Feedback will not be submitted and the message "Feedback cannnot be more then 200 characters" in a pop up displayed; Actual Result: The message "Your Feedback submitted successfully! Thanks for providing your feedback." is displayed at the top of the web page along with a "Back button | Major | Open | Riddhi
D_CI_01 |  | The customer can enter any charcters in address field and that also system takes in | 1) Login to the ewheelz website 2)Click on the UserLogin 3)Click on Book Tickit 4)It will navigate to the customer filling page. 5)There enter the all the valid credentials except the address 5)Click "Save". Data: CustomerName: jay Phone:1234567890 Address:123RTy6(*& Location: Delhi Email: j_M@hotmail.com Gender:Male Expected Result: "Enter the proper address". Actual Result:Redirected to page to the payment details | Major | Open | Jay
D_CP_01 |  | The customer can enter any bank name includiing charcters and numbers | 1) Login to the ewheelz website 2)Click on the UserLogin 3)Click on Book Tickit 4)It will navigate to the customer filling page. 5)There enter the all the valid credentials in customer info 5)Click "Save". 6)It will redirect to the payment details. 7)Eveything will provided from the above information rather bank name and credit card number. 8)Enter the valid card number and invalid bank name. 9)It will direct to the final print of the tickit. Data: Bank Name: 097#@tyw3 credit card number:9876543212345678 Expected Result: "Enter the valid bank" Actual Result:Redirected to page to the print tickit. | Major | Open | Jay
D_ST_01 |  | The URL should not show the Username and password after user logged in | 1)Open eWheelz website 2)Click admin login 3)Watch the URL Data AdminID:Admin Password:admin | Critical | Open | Jenab
D_ST_02 |  | The URL should not show the Username and password after user logged in | 1)Open eWheelz website 2)Open User login page 3)Watch the URL Data Username:vara Password:sai | Critical | Open | Jenab