## Summary
| Overall progress of the QA cycle(Ontime, delayed, Stopped) | On time
| Total number of test cases | 108
| Number of testers | 6
| Test cycle duration | 5 days
Status for 03/22/2013
| Number of test cases planned | 18 | The gap in the total executed and planned can be absorbed by the QA team
| Number of test cases executed | 15
| Number of test cases executed overall | 20
| Number of defects encountered today | 5
| Number of defect encountered so far | 26
| Number of critical defects- still open | 6
Overall status
| Number of test cases planned | 108
| Number of test cases executed | 20
| Pass Percentage of the defects | 98%
| Defects density | 1.73 per day
| Critical defects percentage | 23%
©- SoftwareTestingHelp.com

## Detailed status
Module | Test Case | Scenario | Complexity | Responsible tester | Date of Execution(Can be past, present or future date) | Status(Pass/Fail/blocked/not executed) | Defect ID- Brief description | Severity | Status
Admin | Login | Login | High | Jenab | 2019-03-21 | Fail | DR_AL_01: Runs with nothing written or anything written. | Trivial | Open
Admin | Add Route | Add From_To | Medium | Jenab | 2019-03-21 | Fail | DR_AR_01: Admin login is only not posible so everything is blocked | Major | Blocked
|  | Date | Medium | Jenab | 2019-03-21 | Fail | DR_AR_02: Admin login is only not posible so everything is blocked | Major | Blocked
|  | Only add to one ID | High | Jenab | 2019-03-21 | Fail | DR_AR_03: Admin login is only not posible so everything is blocked | Major | Blocked
Admin | View Route | View Route | Complex | Jenab | 2019-03-21 | Fail | D_VR_01:Admin login is only not posible so everything is blocked | Major | Blocked
|  | Add pickuppoints | Complex | Jenab | 2019-03-21 | Fail | D_VR_02:Admin login is only not posible so everything is blocked | Major | Blocked
Admin | Delete_Route | Delete route by route id | Complex | Harshita | 2019-03-21 | Fail | D_DR_01: Admin login is only not posible so everything is blocked | Major | Blocked
Admin | Delete_Travel | Delete route by travel id | Complex | Harshita | 2019-03-21 | Fail | D_DT_02: Admin login is only not posible so everything is blocked | Major | Blocked
Admin | Font _Size_ViewRoute | Font size is not consistent through out | Medium | Harshita | 2019-03-21 | Fail | D_DR_03: Admin login is only not posible so everything is blocked | Major | Blocked
Admin | View_Travel | ViewTravel_viewRoutes | Complex | Harshita | 2019-03-21 | Fail | D_VT_01:Admin login is only not posible so everything is blocked | Major | Blocked
|  | ViewTravel_addPickuppoint | Complex | Harshita | 2019-03-21 | Fail | D_VT_02:Admin login is only not posible so everything is blocked | Major | Blocked
Admin | Add_Travel | TravelsName | Medium | Harshita | 2019-03-21 | Fail | D_AT_01: Admin login is only not posible so everything is blocked | Major | Blocked
|  | Location | Complex | Harshita | 2019-03-21 | Fail | D_AT_02: Admin login is only not posible so everything is blocked | Major | Blocked
|  | Address | Complex | Harshita | 2019-03-21 | Fail | D_AT_03: Admin login is only not posible so everything is blocked | Major | Blocked
|  | Agent Name | Medium | Harshita | 2019-03-21 | Fail | D_AT_04: Admin login is only not posible so everything is blocked | Major | Blocked
|  | Phone Number | High | Harshita | 2019-03-21 | Fail | D_AT_05: Admin login is only not posible so everything is blocked | Major | Blocked
User | User_Login | User_login | High | Jay Mangnani | 2019-03-21 | Fail | D_US_01: User is not able to login | Critical | Blocked
View Testimonial | VIEWTESTIMONIAL (atleast two testimonial present in the table "feedback") | VIEWTESTIMONIAL | Medium | Riddhi | 2019-03-21 | Pass
Give Testimonials | GIVETESTIMONIAL | GIVETESTIMONIAL | Low | Riddhi | 2019-03-21 | Pass
View Testimonial | VIEWTESTIMONIAL (no testimonial in database table "feedback") | VIEWTESTIMONIAL | Low | Riddhi | 2019-03-21 | Pass
Give Testimonials | GIVETESTIMONIAL | GIVETESTIMONIAL | Medium | Riddhi | 2019-03-21 | Pass
Give Testimonials | GIVETESTIMONIAL | GIVETESTIMONIAL | Medium | Riddhi | 2019-03-21 | Fail | D_GT_03: No error message is displayed eventhough the feedback provided exceeds the limit, D_GT_02: The feedback more then 200 characters given is added into the table named as feedback in the database | Major | Open
Give Testimonials | GIVETESTIMONIAL | GIVETESTIMONIAL | Medium | Riddhi | 2019-03-21 | Pass
Give Testimonials | GIVETESTIMONIAL | GIVETESTIMONIAL | Medium | Riddhi | 2019-03-21 | Fail | D_GT_03: No error message is displayed eventhough the feedback provided exceeds the limit, D_GT_02: The feedback more then 200 characters given is added into the table named as feedback in the database | Major | Open
Give Testimonials | GIVETESTIMONIAL | GIVETESTIMONIAL | Low | Riddhi | 2019-03-21 | Fail | D_GT_04: System is taking wrong email ID format and update database with the wrong/non exist email ID. | Medium | Open
View Route | View Route | View Route | Medium | Jay Patel | 2019-03-21 | Pass
Book Ticket | Book_Ticket | To | High | Sohana Kadiwala | 2019-03-21 | Fail | D_BT_01:User is not able to book tickets as Calender is not working to select journey date | Trivial | Blocked
|  | From | High | Sohana Kadiwala | 2019-03-21 | Fail | D_BT_02:User is not able to book tickets as Calender is not working to select journey date | Critical | Blocked
|  | Journey_Date | High | Sohana Kadiwala | 2019-03-21 | Not Executed | D_BT_03:User is not able to book tickets as Calender is not working to select journey date | Critical | Blocked
|  | Bus_Type | Medium | Sohana Kadiwala | 2019-03-21 | Fail | D_BT_04:User is not able to book tickets as Calender is not working to select journey date | Critical | Blocked
|  | No. of Passenger | Low | Sohana Kadiwala | 2019-03-21 | Fail | D_BT_05:User is not able to book tickets as Calender is not working to select journey date | Critical | Blocked
Cancel_Ticket | Cancel_Ticket | Ticket_ID | Medium | Sohana Kadiwala | 2019-03-21 | Fail | D_BT_06:User is not able to cancel tickets as cancelling ticket showing blank screen | Critical | Blocked
Customer_detail | Customer_Detail_Inv_Address | Address | Medium | JayMangnani | 2019-03-27 | Fail | D_CI_01: It takes the address with the charcters also | Major | Blocked
Customer_payment_detail | Customer_Payment_Inv_Bankame | BankName | High | JayMangnani | 2019-03-27 | Fail | D_CP_01: It take the number , charcters as the bank name | Crtical | Blocked

## Bug Report Test Cycle 1
Defect ID | Test Script ID | Defect Description | Steps to reproduce | Severity | State | Created by | Assigned to
DR_AL_01 | TC_ADMIN_LOGIN_INV_001-008 | The username and password fields does not take any values and just directed to admin page and also if we write anything in both fields it will be directed to the admin page. | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page". Actual Result: "Does not login" | Critical | Open | Jenab
DR_AR_01 | Test Case - TC_ADDROUTE_VAL_001 | It should let the Admin enter "add route" in the module of admin but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page". Actual Result: "Does not login" | Major | Blocked | Jenab
DR_AR_02 | Test Case - TC_ADDROUTE_VAL_001 | It should let the Admin enter "add route" in the module of admin but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page". Actual Result: "Does not login" | Major | Blocked | Jenab
DR_AR_03 | Test Case - TC_ADDROUTE_VAL_001 | It should let the Admin enter "add route" in the module of admin but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on Add Travel" Actual Result: "Does not login" | Major | Blocked | Jenab
D_VR_01 | Test Case - TC_VIEWROUTE_VAL_001 | It should let the admin enter in "view route" in the module of admin but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on View Route" Actual Result: "Does not login" | Major | Blocked | Jenab
D_VR_02 | Test Case - TC_VIEWROUTE_VAL_001 | It should let the admin enter in "view route" in the module of admin but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on View Route" Actual Result: "Does not login" | Major | Blocked | Jenab
D_DR_01 | Test Case - TC_DELETEROUTE_VAL_001 | It should let the admin in the "delete route" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on DeleteRoute" Actual Result: "Does not login" | Major | Blocked | Harshita
D_DT_02 | Test Case - TC_DELETETRAVELROUTE_VAL_001 | It should let the admin in the "delete travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on DeleteTravel" Actual Result: "Does not login" | Major | Blocked | Harshita
D_DR_03 | Test Case - TC_DELETEROUTE_VAL_001 | It should let the admin in the "delete route" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on DeleteRoute" Actual Result: "Does not login" | Major | Blocked | Harshita
D_VT_01 | Test Case - TC_VIEWTRAVELROUTE_VAL_001 | It should let the admin in the "view travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on ViewTravel" Actual Result: "Does not login" | Major | Blocked | Harshita
D_VT_02 | Test Case - TC_VIEWTRAVELROUTE_VAL_001 | It should let the admin in the "view travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on ViewTravel" Actual Result: "Does not login" | Major | Blocked | Harshita
D_AT_01 | Test Case - TC_ADDTRAVELROUTE_VAL_001 | It should let the admin in the "Add Travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on AddTravel" Actual Result: "Does not login" | Major | Blocked | Harshita
D_AT_02 | Test Case - TC_ADDTRAVELROUTE_VAL_001 | It should let the admin in the "Add Travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on AddTravel" Actual Result: "Does not login" | Major | Blocked | Harshita
D_AT_03 | Test Case - TC_ADDTRAVELROUTE_VAL_001 | It should let the admin in the "Add Travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on AddTravel" Actual Result: "Does not login" | Major | Blocked | Jenab
D_AT_04 | Test Case - TC_ADDTRAVELROUTE_VAL_001 | It should let the admin in the "Add Travel" of admin module but it does not log in by the username and password | 1)Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on AddTravel" Actual Result: "Does not login" | Major | Blocked | Jenab
D_AT_05 | Test Case - TC_ADDTRAVELROUTE_VAL_001 | It should let the admin in the "Add Travel" of admin module but it does not log in by the username and password | 1) Login to the ewheelz website 2)Click on the AdminLogin 3)Add the username and password. 4)Click on"Go" 5)Directed to the admin page. Data : Username :admin Password:admin Expected Result: "Directed to admin Page and Click on AddTravel" Actual Result: "Does not login" | Major | Blocked | Harshita
D_US_01 | TC_USER_LOGIN_VAL_001-008 | User is not able to login with username and password | 1) Goto http:/localhost:8080/ewheelz/Login.jsp 2) Add username and password 3)Click on"Go" 4) No response user not able to login Data: Username : vara Password: sai Expected Result: "Directed to the Homepage". Actual Result : "User not able to login". | Critical | Open | Jay Mangnani
D_GT_01 | TS_INV_GT_04 | No error message is displayed eventhough the feedback provided exceeds the limit | 1: Goto the link http:///ewheelz/User.html 2: Click on User Login 3: Click on Give Testimonial button on the left side of the web page 4: Enter the emai Id "abc123@gmail.com"text in the "email Id" field 5: Enter the feedback (more than 200 characters) in the feedback field 6: Click on Submit Feedback button; Expected Result: Feedback will not be submitted and the message "Feedback cannnot be more then 200 characters" in a pop up displayed; Actual Result: The message "Your Feedback submitted successfully! Thanks for providing your feedback." is displayed at the top of the web page along with a "Back button | Major | Open | Riddhi
D_GT_02 | TS_INV_GT_04 | The feedback more then 200 characters given is added into the table named as feedback in the database | 1: Goto the link http:///ewheelz/User.html 2: Click on User Login 3: Click on Give Testimonial button on the left side of the web page 4: Enter the emai Id "fk123@gmail.com"text in the "email Id" field 5: Enter the feedback (more than 200 characters) in the feedback field 6: Click on Submit Feedback button; Expected Result: Feedback will not be saved in the table "feedback" in the data base; Actual Result: The message "Your Feedback submitted successfully! Thanks for providing your feedback." is displayed at the top of the web page along with a "Back button and the feedback given is added into the table named as feedback in the database | Major | Open | Riddhi
D_GT_03 | TS_V_GT_01 | System is taking wrong email ID format and update database with the wrong/non exist email ID. | 1.Click on the given link to open the testimonial page. 2.Click on email id to enter the email id. 3.Click on feedbak field to type the feedback. 4. Click on submit button to submit the feedback. 5.Verify with the database whether it is updated or not. | Minor | Open | Riddhi
D_GT_04 | TS_INV_GT_04 | No error message is displayed eventhough the feedback provided exceeds the limitC26 | 1: Goto the link http:///ewheelz/User.html 2: Click on User Login 3: Click on Give Testimonial button on the left side of the web page 4: Enter the emai Id "abc123@gmail.com"text in the "email Id" field 5: Enter the feedback (more than 200 characters) in the feedback field 6: Click on Submit Feedback button; Expected Result: Feedback will not be submitted and the message "Feedback cannnot be more then 200 characters" in a pop up displayed; Actual Result: The message "Your Feedback submitted successfully! Thanks for providing your feedback." is displayed at the top of the web page along with a "Back button | Major | Open | Riddhi
D_BT_01 to D_BT_12 | TC_BT-001 to TC_BT-012 | User is not able to book tickets as Calender is not working to select journey date | 1) Login to the ewheelz website 2)Click on the UserLogin 3)Click on Book Ticket 4)Select "To" and "From" the dropdown list 5)Select "Journey date" from the calender 6)Select "Bus Type" 7)Select "No. of Passenger" 8)Click "Continue" button Expected Result: Redirect to next page Actual Result: User is not able to book tickets as Calender is not working to select journey date | Major | Blocked | Sohana
D_CT_01 to | TC_BT-001 to TC_BT-012 | User is not able to cancel tickets as cancelling ticket showing blank screen | 1) Login to the ewheelz website 2)Click on the UserLogin 3)Click on Cancel Ticket 4)Enter Ticket ID 5)Click "Cancel Ticket" Button Expected Result: Redirected to page to select the ticket which is selected to be cancelled Actual Result: The Redirected page appear blank | Major | Blocked | Sohana
D_CI_01 |  | The customer can enter any charcters in address field and that also system takes in | 1) Login to the ewheelz website 2)Click on the UserLogin 3)Click on Book Tickit 4)It will navigate to the customer filling page. 5)There enter the all the valid credentials except the address 5)Click "Save". Data: CustomerName: jay Phone:1234567890 Address:123RTy6(*& Location: Delhi Email: j_M@hotmail.com Gender:Male Expected Result: "Enter the proper address". Actual Result:Redirected to page to the payment details | Major | Open | Jay
D_CP_01 |  | The customer can enter any bank name includiing charcters and numbers | 1) Login to the ewheelz website 2)Click on the UserLogin 3)Click on Book Tickit 4)It will navigate to the customer filling page. 5)There enter the all the valid credentials in customer info 5)Click "Save". 6)It will redirect to the payment details. 7)Eveything will provided from the above information rather bank name and credit card number. 8)Enter the valid card number and invalid bank name. 9)It will direct to the final print of the tickit. Data: Bank Name: 097#@tyw3 credit card number:9876543212345678 Expected Result: "Enter the valid bank" Actual Result:Redirected to page to the print tickit. | Major | Open | Jay